## Project schedule
| CIVE 202 Project #3 | [5 empty] | Project start: | [7 empty] | 2026-02-27
| Anicet Atikpohou | [5 empty] | Display week: | [7 empty] | 1
[7 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-05
 | time axis 2026-02-23 to 2026-04-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Github Repository
| Create Github | Anicet | 0% | 2026-02-27 | 2026-03-02 | 4
| Create README Document | Anicet | 0% | 2026-02-27 | 2026-03-05 | 7
| Combine information/Files | Anicet | 0% | 2026-02-27 | 2026-03-05 | 7
| Upload All Files to Github | Anicet | 0% | 2026-02-27 | 2026-03-27 | 29
| Submit | Anicet | 0% | 2026-02-27 | 2026-03-30 | 32
Scope of Work
| Identify Tasks | Anicet | 100% | 2026-02-25 | 2026-02-27 | 3
| Create SOW | Anicet | 100% | 2026-02-25 | 2026-02-27 | 3
| Review | Anicet | 0% | 2026-02-27 | 2026-03-28 | 30
| Submit SOW | Anicet | 0% | 2026-02-25 | 2026-03-26 | 30
Gantt Chart
| Identify Tasks | Anicet | 100% | 2026-02-25 | 2026-02-27 | 3
| Create Gantt Chart | Anicet | 100% | 2026-02-25 | 2026-03-27 | 31
| Review | Anicet | 0% | 2026-02-25 | 2026-03-29 | 33
| Turn in Gantt Chart | Anicet | 0% | 2026-02-24 | 2026-03-29 | 34
Visualization
| Charts/ Graphs | Anicet | 0% | 2026-02-27 | 2026-03-29 | 31
| IDM Visualization | Anicet | 0% | 2026-02-27 | 2026-03-29
| Discuss/Apply To Report | Anicet | 0% | 2026-02-27 | 2026-03-29 | 31
Python Code
| LAB 1 Material | Anicet | 0% | 2026-02-27 | 2026-03-06 | 8
| LAB 2 Material | Anicet | 0% | 2026-03-06 | 2026-03-13
| LAB 3 Material | Anicet | 0% | 2026-03-13 | 2026-03-24
| LAB 4 Material | Anicet | 0% | 2026-03-24 | 2026-03-27
| Combine/Polish | Anicet | 0% | 2026-03-27 | 2026-03-31
| Review and Submit | Anicet | 0% | 2026-03-28 | 2026-03-31
Annotated Code Document
| LAB 1 Material | Anicet | 0% | 2026-02-27 | 2/29/26 | #VALUE!
| LAB 2 Material | Anicet | 0% | 2/29/26 | 2026-03-07
| LAB 3 Material | Anicet | 0% | 2026-03-07 | 2026-03-15
| LAB 4 Material | Anicet | 0% | 2026-03-15 | 2026-03-28
| Combine/Polish | Anicet | 0% | 2026-03-27 | 2026-03-31
| Review and Submit | Anicet | 0% | 2026-03-28 | 2026-03-31
Written Report
| Analyze Outputs | Anicet | 0% | 2026-03-11 | 2026-03-29 | 19
| Create Document to Standards | Anicet | 0% | 2026-03-29 | 2026-04-06
| Review | Anicet | 0% | 2026-03-25 | 2026-03-30
| Submit | Anicet | 0% | 2026-03-24 | 2026-03-31